## Slide 1: Agile Estimation
Stephen Forte @worksonmypc
Chief Strategy Officer
Telerik
DPR202

## Slide 2: Bio
Chief Strategy Officer of Telerik
Certified Scrum Master
21st TechEd of my career!
Active in the community:
  International conference speaker for 12+ years
  RD, MVP and INETA speaker
  Co-moderator and Founder of NYC .NET Developers Group http://www.nycdotnetdev.com
  Wrote a few books: SQL Server 2008 Developers Guide (MS Press)
MBA from the City University of New York
Past:
  CTO and Co-Founder of Corzen, Inc. (TXV: WAN)
  CTO of Zagat Survey
Notes: 2

## Slide 3: Agenda
The Estimation Problem
Agile Estimation
Q&A

## Slide 4: Agenda
The Estimation Problem
Agile Estimation
Q&A

## Slide 5: Estimation
    Problem is that estimates become a unbreakable schedule, where any deviation is considered bad
“Estimation is the calculated approximation of a result which is usable even if input data may be incomplete or uncertain.”
— Wikipedia

## Slide 6: Problem #1 with Estimates
Estimate for our project
  One month for design and architecture
  Four months for development
  One month for testing
Scenario
  Your first estimate is wrong by one week (design)
  What do you do?

## Slide 7: The Estimation Problem
When you come up with a project idea, your first estimate is off by +/4x
  Not enough details are known
Traditionally too much time is spent on building a specification which is not complete
  Again, not enough details are known
As time progresses, more details emerge about the system and its details
  The cone of uncertainty

## Slide 8: The Cone of Uncertainty
4x |  |  |  |  |  |  |  |  |  | 
2x |  |  |  |  |  |  |  |  |  | 
1.5x |  |  |  |  |  |  |  |  |  | 
1.25x |  |  |  |  |  |  |  |  |  | 
1.0x |  |  |  |  |  |  |  |  |  | 
.8x |  |  |  |  |  |  |  |  |  | 
.67x |  |  |  |  |  |  |  |  |  | 
.5x |  |  |  |  |  |  |  |  |  | 
25x |  |  |  |  |  |  |  |  |  | 
Estimate of Variability
Time
Initial Concept
Approved Product Definition
User Interface Design Complete
Detailed Design Complete
Requirements Complete
Software Complete

## Slide 9: Agenda
The Estimation Problem
Agile Estimation
Q&A

## Slide 10: Agile Estimation
Wikipedia: Estimation is the calculated approximation of a result which is usable even if input data may be incomplete or uncertain
  Problem is that estimates become an unbreakable schedule, where any deviation is considered bad
Agile Estimation throws this logic away and always re-estimates a project after each iteration
  Different value system, deviations are not deviations, they are more accurate estimations
  Uses the cone of uncertainty to your advantage

## Slide 11: How to Estimate
User stories
Planning poker
Story points
Product backlog
Velocity
Re-estimation

## Slide 12: User Stories
Users break down the functionality into “user stories”
User stories are kept small
User stories include acceptance criteria

## Slide 13: Planning Poker
After all the user stories are written, get a list of stories and do a high level estimate
  Estimate is for setting priorities, not schedule
NOT a time based estimation
  Super hard, hard, medium, easy, and super easy
Done by consensus
  To get there, you play “planning poker”
  Why? No pressure

## Slide 14: Story Points
Break down user stories to units of relative size
  So you can compare features
  Alternative to time
Story points are not a measurement of duration, but rather a measurement of size/complexity
Start with 1 standard feature and then other features are either 1x, 2x, etc. larger or smaller than that relative feature in size/complexity

## Slide 15: Product Backlog
All story points are put into a bucket
This represents all of the tasks for the project (work items)
Backlog will have an item and its estimate
  Remember this estimate is not time based, but point based
Backlog can also contain the priority

## Slide 16: A Sample Product Backlog
Backlog item | Estimate
Allow a guest to make a reservation | 3
As a guest, I want to cancel a reservation | 5
As a guest, I want to change the dates of a reservation | 3
As a hotel employee, I can run RevPAR reports (revenue-per-available-room) | 8
Improve exception handling | 8
... | 30
... | 50

## Slide 17: Sprint 1
Developers will commit to XX story points
Warning, they will usually overcommit
After the end of sprint one, you have your first velocity number

## Slide 18: Team Velocity
Velocity is the number of story points per sprint completed
You calculate velocity to predict how much work to commit to in a sprint
Velocity only works if you estimate your story points consistency
Over time you will know: team has a velocity of 32 story points per sprint
  Over time this will self-correct
  Over time you will be able to predict the project schedule (and release)

## Slide 19: Calculating Team Velocity
Select a regular time period (sprint) over which to measure velocity
Add up the story point estimates 100% completed
At the end of the sprint, the figure you have is your velocity
You can then use your velocity as a basis for your future commitments

## Slide 20: Re-estimation
As you complete more sprints, your velocity will change
  Velocity changes because of minor inconsistencies in the story point estimates
  Team velocity will typically stabilize between three and six iterations
Re-estimation of the entire project happens after each sprint
  New velocity
  New story points added and removed (completed)
  Use the cone!

## Slide 21: Reading List
Books I have read and recommend:
User Stories Applied by Mike Cohn
Agile Estimating and Planning by Mike Cohn
Agile Retrospectives by Esther Derby and Diana Larsen

## Slide 22: DPR Track Resources
http://www.microsoft.com/visualstudio
http://www.microsoft.com/visualstudio/en-us/lightswitch
http://www.microsoft.com/expression/
http://blogs.msdn.com/b/somasegar/
http://blogs.msdn.com/b/bharry/
http://www.microsoft.com/sqlserver/en/us/default.aspx
http://www.facebook.com/visualstudio

## Slide 23: Resources
www.microsoft.com/teched
  Sessions On-Demand & Community
  Microsoft Certification & Training Resources
  Resources for IT Professionals
  Resources for Developers
www.microsoft.com/learning
http://microsoft.com/technet
http://microsoft.com/msdn
Learning
http://northamerica.msteched.com
  Connect. Share. Discuss.

## Slide 24
Complete an evaluation on CommNet and enter to win!