## Slide 1: Apollo - Software Development Lifecycle
25 July 2018
V0.3

## Slide 2: SSP – Target SDLC
Product
Customer
Service
Demand
Framework
Scrum
Kanban
Deploy
Portfolio Backlog
ALM Tools
Notes: Adopt an Agile process across the business using ALM tools to support process change
Framework – options depending on nature of demand
Cross-discipline, cross-application teams
Collaborative working
Common processes & tools across the business
ALM tools
  Support process & provide standard metrics
Philosophy to Empower teams – accountability & self-improvement
Focus on
  delivering value as soon as possible
  continuous improvement
SAFe – Scaled Agile Framework
Team/Programme/Portfolio

## Slide 3: Timeline
Solution Validation outputs to change:
Epics and Features (more than today)
Soln. Validation to be reviewed
Iteration
-n -2 -1 0 1 2 3
Solution Validation
OOM Estimates
OOM estimates using todays estimating approaches
Future – H.L. Estimating model for each product
Output is Team Size & (for Sales) rough Duration/ Cost
Initiation
Skeleton team
Skeleton team :
TDM
Arch.
BA
Lead Dev
Lead Test
Notes: Initiation – identify MVP, delivery order & estimate

## Slide 4: Initiation
Solution Validation Epics
Backlog
Prioritised Backlog
Estimated Backlog
High Level Plan
6a
3a
6
5
4
3
2
1
MVP
Non MVP
2
8 (6b)
7 (3b)
5
4
1
OOM estimated epics on Backlog
Identify MVP and re-state epics
Prioritise delivery of epics
Ideal day estimates generated using Estimating Model
Indicative plan created based on priority order, estimates & team size
6a
3a
MVP
Non MVP
2
5
8 (6b)
1
7 (3b)
4
Agreed Team Size
6a
3a
MVP
Non MVP
2
5
8 (6b)
1
7 (3b)
4
Notes: Ideally we wouldn’t create a plan at this stage – too big a change for SSP today?

## Slide 5: Timeline
Solution Validation outputs to change:
Epics and Features (more than today)
Soln. Validation to be reviewed
Iteration
-n -2 -1 0 1 2 3
Create Stories
Solution Validation
OOM Estimates
OOM estimates using todays estimating approaches
Future – H.L. Estimating model for each product
Output is Team Size & (for Sales) rough Duration/ Cost
Initiation
Team agree stories should be created 2 sprints ahead initially – moving to 1 ahead as we mature
Skeleton team
Skeleton team :
TDM
Arch.
BA
Lead Dev
Lead Test
Notes: Initiation – identify MVP, delivery order & estimate
Create Stories – Arch & BA tech design & requirements then walkthrough with team to create stories

## Slide 6: Story Creation
Technical Design
Initial Stories
Review & Estimate
Agreed & Estimated Stories
Story 1
2
Prioritised Backlog
6a
3a
MVP
Non MVP
2
5
8 (6b)
1
7 (3b)
4
2
Architect
takes Epics in order & completes technical design (in VSTS tickets)
BA / Lead Dev contribute.
Story 2
Story 3
Story 1
Story 2
Story 3
Story 4
2
Walkthrough with the delivery team to agree stories & estimate
Stories proposed
& Requirements documented in VSTS tickets). BA led with Lead Dev, Lead Tester contributing.
Backlog updated

## Slide 7: Timeline
Solution Validation outputs to change:
Epics and Features (more than today)
Soln. Validation to be reviewed
Iteration
-n -2 -1 0 1 2 3
Iteration 0 tasks
Create Stories
Deliver
Deliver
Deliver
Create Stories
Ready for UAT:
Create Stories
Create Stories
Create Stories
Solution Validation
OOM Estimates
OOM estimates using todays estimating approaches
Future – H.L. Estimating model for each product
Output is Team Size & (for Sales) rough Duration/ Cost
Initiation
Team agree stories should be created 2 sprints ahead initially – moving to 1 ahead as we mature
Skeleton team
Skeleton team :
TDM
Arch.
BA
Lead Dev
Lead Test
Full team
Notes: Initiation – identify MVP, delivery order & estimate
Create Stories – Arch & BA tech design & requirements then walkthrough with team to create stories
Iteration 0
Any technical tasks necessary for project development to start, e.g. Code repository creation/Proof of Concept work/Tool set-up
Deliver – acceptance criteria/TDD/functional test
CI/CD through integration & NFT - auto tests

## Slide 8: Agile Process
Supports the rapid delivery of high quality software that aligns with company goals and customer needs
Sprint Planning
Product Backlog
Sprint Backlog
Product Increment
Sprint Review
Sprint Retro
Notes: Quality gates – ensure quality input into & out of sprints
Engineering best practices
DevOps principles – Ops & Service working with dev teams through whole process

## Slide 9: Sprint Planning & Backlog
Sprint Planning
Quality gate – Definition of Ready
User Stories – functional slices, 2-3 days to complete
Story Points
Estimates
Sprint backlog – achievable but challenging
Team commit to completing all items in iteration
Notes: Quality gates – ensure quality input into & out of sprints
--------------------------------------------------------------------------
User Stories – right level……. Complete in sprint…. functional slices…… deliver business value
Team agree scope all tasks identified
Points – planning poker
Estimates – all tasks
Sprint backlog
Achievable - can complete all User Stories
  Challenging enough to keep all team members busy

## Slide 10: Deliver Stories
Sprint Duration
Team collaboration on sprint backlog
Daily stand-up to discuss risks & issues
Acceptance criteria – BA & Tester
TDD/BDD
Build in repeatable automated tests with each User Story
Continuous Integration/Deployment
Build created & Unit tests run each check-in
Automated functional tests run every day
E2E release pipeline
Aligned environments across products
Integration testing & NFT testing continuous – aim for daily
Definition of Done
ALM tools updated throughout
Notes: Acceptance Criteria – analysts & testers – gherkin syntax – given/when/then
TDD/BDD
Unit tests - xUnit – Nunit/JUnit
EMBED QUALITY!
Automated tests – functional, integration, nft
Pipeline: dev –> system test -> Integration -> NFT/Performance
Feature switches
DoD – know work is complete when leaves sprint

## Slide 11: Changes
Sprint End
Sprint Review
  Review Sprint output
  Confirm incremental business value to the product
  Feedback – amendments to Product Backlog
Product Increment
  Release pipeline – where next?
Sprint Review
Sprint Retro
Sprint Retrospective
  Review metrics
  Identify Improvements
Metrics
Notes: Review – Showcase/demo/show & tell – to product owner
Release pipeline – where next?
Customer constraints – UAT at agreed time
True services UAT -> preprod -> prod for e.g. PRE/Verify
Retro:
Review burndown/up -> Actual vs estimates
What went well/not -> identify improvements
Results of past improvements?
Metrics – burndowns/ups – sprint/feature/epic/release
Velocity…. Actuals vs estimates……. Committed vs completed….. Etc

## Slide 12: Kanban
Care & Maintenance
Backlog prioritised
Work items picked up by priority
Mixed discipline teams
Daily stand-ups

## Slide 13: Deployment

## Slide 14: Continuous Improvement
A Process to review the process……
Continuous Improvement applies to the agile process implemented
Review & change where benefit can be gained
Process to review ALM changes
Regular review of processes
Review Feedback
Retrospective improvements reviewed
  Identify those to be adopted company-wide
Notes: Review process
Quarterly retrospective of process
Backlog for ALM changes