## Slide 1: Agile – Estimation

## Slide 2: Estimation
Product team break down the functionality into Epic/Feature/UserStory
Planning Poker is to be used as relative estimation technique
Fibonacci Sequence will be used for Story Points
Story Point of first user story will be used as base line for the relative estimation of rest of the stories
Story points will be based on the size/complexity rather than duration
Everybody reveals estimate simultaneously
Lowest and highest estimator justifies
Team decides on collective estimate
Total of story points of all user stories included in release/Project will define the scope of Release/Project
Team Velocity will be the sum of total story points of 100% completed user stories in a sprint
Team Velocity will stabilize in 3 to 6 sprints
Release/Project duration will be calculated by dividing “Total release/Project story points/Team Velocity”
Re-estimation of release will be done as and when Scrum Master thinks appropriate
Actual Effort estimation will be done once we decide the team velocity
Actual Estimation = Person Days/ Team velocity * Total release/Project story points
Sprint | Duration (In Weeks) | Team Size | Story Point Completed | Person Days
1 | 2 | 5 | 10 | 50
2 | 2 | 5 | 15 | 50
3 | 2 | 5 | 12 | 50
4 | 2 | 5 | 11 | 50
5 | 2 | 5 | 11 | 50
Team Velocity = 11 Story Points Per Sprint
Actual Effort Per Story Point = 50/11 = 4.55 PDs

## Slide 3: Estimation
Occurrence | Input(s) | Tools | Output(s) | Participants
Project | Total number of User Stories included in a Project Team Velocity | Fibonacci Sequence | Project Level Estimate | Domain Experts Product Owener Team Members Scrum Master
Release | Prioritize Backlog Items (Product Backlog) included in a Release Team Velocity | Fibonacci Sequence | Release Level Estimate | Product Owner Team Members Scrum Master
Sprint | User Stories assigned to sprint during sprint planning | Planning Poker Fibonacci Sequence Story Points | Sprint Level Estimate | Product Owner Team Members Scrum Master

## Slide 4: Level of Estimation
Project
Activity: Project Level Estimation
Participants: Domain Experts/Team Members/Scrum Master
Release
Activity: Release Level Estimation
Sprint
Activity: Sprint Level Estimation
Outcome: High Level Estimate
Input: Project Requirement
Tools and Technology : Functional Points
Participants: Product Owner/Team Members/Scrum Master
Input: Prioritize Backlog Items (Product Backlog)
Tools and Technology : Poker Planning, Story Points
Outcome: Total no of story points covered in a release
Participants: Product Owner/Team Members/Scrum Master
Input: User Stories assigned to sprint during sprint planning
Tools and Technology : Story Points
Outcome: Total no of story points covered in a sprint